## Slide 1
Project Monitoring & Control
  Development process training
aug. 2021
Rev 2.00
Sw division & qa division
Renesas design vietnam

## Slide 2: Agenda
Purpose of Monitoring and Control Page 03
Change management Page 06
Risk and problem management Page 14
Defect management Page 17
Progress management Page 26

## Slide 3
Purpose of monitoring and control

## Slide 4: Purpose of Monitoring and Control purpose and judgement criteria
Monitor the project status according to the project plan based on the defined criteria
Implement measures for a deviation from a project plan on a timely manner
Project Plan
Criteria of deviations
Describe the criteria of deviation for judging that it is necessary to carry out the appropriate works
Notes: 【Example】 The criteria of deviation are below.
  1. In case the actual man-hour in that process measured at the end of each process is higher than planned effort by 30% or more.
  2. In case the actual end of date of each process is delayed than planned date by 1 month or more.

## Slide 5: Purpose of Monitoring and Control management items
Configuration & Change Management
Risk & Defect Management
Progress Management
To ensure that the project requirements and work products are changed, added, and deleted,
and to maintain that there is no excess, deficiency, and inconsistency between requirements and work products
To reduce and eliminate impacts that hinder the achievement of the project objectives, to identify and analyze the defects detected in reviews and tests, and to implement corrective actions to resolve the defects
To confirm the progress of the project and deviation from the plan and to implement appropriate measures
Notes: Configuration management to be introduced at the training of topic #5.

## Slide 6
Change management

## Slide 7: change management procedure
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 8: change management procedure reception
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The person responsible for requirement/change management
Project members
Action
Apply for addition, change or deletion according to the management policy of the project plan
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 9: change management procedure recording
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The person responsible for requirement/change management
Action
Record the ID, requester, date and content of change request
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 10: change management procedure analysis the impact
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The person responsible for requirement/change management
The development-related persons and other interested persons
Action
Analyze the impact the change has on work products and the development plan
Record the analysis result to Change Management Table
traceability
Notes: The mechanism of traceability is used to specify the range of the impact on work products. For the use of traceability, see "8. Traceability Management Procedure".
Note that the role and appointment of the person responsible for requirement/change management are in accordance with "16. Formulation of the Project Plan", in "Operation Standard for Software Development Process" (RCT-JB5001).

## Slide 11: change management procedure evaluation and planning
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The project leader
The person responsible for requirement/change management
Action
Determine the feasibility: to be implemented or escalated the issue to the PL/PM for resolution
Decide and record: implementation schedule, content and PIC of the change
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 12: change management procedure implementation
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The person responsible for requirement/change management
Action
Implement the change
Hold peer review, record the result to Change Management Table and obtain approval from the PL
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 13: change management procedure monitoring and control
Reception
Evaluation and planning
Monitoring and control
Implementation
Recording
Analysis the impact
Person in charge
The project leader
The person responsible for requirement/change management
Action
Check the change in request and the status of change request (investigating, ongoing, verifying, completed, or rejected)
Make the appropriate correction if the change is not implemented as planned
Notes: The change of the work product caused by defect correction is managed in accordance with “Procedure for Defect Management” in “Software Development Implementation Standard for Risk and Defect Management”.

## Slide 14
Risk and problem management procedure

## Slide 15: risk and problem management procedure identify and monitor
Evaluate
Treat
Monitor
Identify
Evaluate risk level
Define
mitigation plan
Conduct review
Agree?
No
Yes
Process asset
Project context
Common risk/problem assessment
Implement and regularly check
Identify risks/problems
Risk and Problem Management Table / Redmine
When implement risk management, project should regularly check (at the progress confirmation meeting or another opportunity) and re-evaluate risk level. After that, mitigation plan can change to be suitable with risk level at determined time.

## Slide 16: risk and problem management procedure evaluate and treat
Degree of impact | Description
Large (5) | Impact of the problem reaches the customers outside the Renesas Electronics group
Medium (4) | Impact of the problem reaches the release destinations within the Renesas Electronics group
Small (2) | Impact of the problem reaches inside the project
Severity | Action
>= 20 | Taking a risk mitigation measure
>= 15 | Planning a problem-solving measure
>= 12 | Planning a risk mitigation measure
>= 6 | Monitoring the risk in the progress confirmation meeting
< 6 | No monitoring. But confirm before each design review (DR checklist)
Potentiality of being problem | Description
High (5) | The risk is highly likely to develop into a problem
Medium (3) | The risk is likely to develop into a problem
Low (2) | The risk is not likely to develop into a problem
Problem (15) | The risk has developed into a problem
multiply
Notes: level < 6: ko cần monitor. (còn việc "confirm before each DR" thì trong DR checklist có 1 checkpoint liên quan tới này)
6 <= level < 12: cái risk này cần đc monitor và confirm status trong buổi progress confirmation meeting
12 <= level < 15: plan cái measure(s) để giảm thiểu cái risk này
15 <= level < 20: đặt trường hợp cái risk này trở thành vấn đề thì measure(s) để giải quyết là gì (plan cái measure(s) giải quyết vấn đề)
level >= 20: thực hiện cái measure(s) ngay và luôn để giảm thiểu cái risk này.
level 15: nôm na chỉ mới dừng lại ở bước planning (và đương nhiên chú ý planning này là planning measure(s) giải quyết vấn đề, ko phải planning giảm thiểu risk) (kiểu kiểu giống như tương lai sẽ làm nếu có xảy ra)
level 20: làm ngay cái measure(s) để giảm thiểu cái risk này (kiểu kiểu giống như hiện tại cái risk nguy cơ quá cao rồi... phải làm ngay (những) cái gì đó (measure(s)) để giảm thiểu cái risk này xuống (giảm xuống 15 hoặc nhỏ hơn nữa chẳng hạn thì chỉ cần planning thôi).

## Slide 17
Defect management procedure

## Slide 18: Definition of defect
Defect
Document
Source code
Item or description that does not comply with or meet a request, requirement (functional or non-functional requirement) and design specification for previous process.
Unclear description subject to misinterpretation by other people
Coding inconsistent with the Design Document and Coding convention
Duplicate defects (defects that require correction in several places due to use of same description and same methods) will be treated as a single defect.
Errors such as typo or omitted characters are not counted.

## Slide 19: Defect management Target
Implement analysis and management for detected defects
Ensure quality of the work products
Record and utilize defect analysis results as process assets

## Slide 20: Defect management procedure Report and Record the defect
Report and Record the defect
Consider and decide defect correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The person in charge who creates the work product
The person in charge who performs the test
Action
Report to the defect manager
Record in the tool or the Defect Management Table

## Slide 21: Defect management procedure Determine the urgency of defect
Report and Record the defect
Consider and decide defect correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The project leader
Action
Determine and record the urgency of resolving the defect
criteria
Quickly holds a meeting to confirm the validity of the result of the judgment result
high
normal
Criteria: The defect causes a delay in the release of the product to the customer and a large lack for a customer's requirement

## Slide 22: Defect management procedure Determine the resolve procedure for defect
Report and Record the defect
Consider and decide defect correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The person in charge who creates the work product
Action
Follow the procedure described in “Consider and Decide the correction method for defect”, “Correct defect” and “Confirm the result of correcting the defect”

## Slide 23: Defect management procedure Consider and Decide the correction method for defect
Report and Record the defect
Consider and Decide the correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The person in charge who creates the work product
Action
Consider and decide the correction method in view of performance (speed, size) and maintainability
If the correction method impacts to the work products of other processes, a meeting is held with the related persons

## Slide 24: Defect management procedure Correct defect
Report and Record the defect
Consider and Decide the correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The person in charge who creates the work product
Action
Correct the defect according to the defect correction method
Record the category of correction (corrected, unreproducible, falsely recognized, or constrained), version after correction and completion date

## Slide 25: Defect management procedure Confirm the result of correcting the defect
Report and Record the defect
Consider and Decide the correction method for defect
Confirm the result of correcting the defect
Correct defect
Determine the urgency of defect
Determine the resolve procedure for defect
Person in charge
The person in charge who creates the work product
The project leader
Action
Hold a progress confirmation meeting to confirm that all defects have been resolved according to the defect correction method
Record the confirmation date

## Slide 26
Progress management

## Slide 27: Progress management policy
Project Plan
Progress management policy
Timing of execution (daily, weekly, etc.)
Use of tools or forms
Update/change/cancellation of the project plan if the progress status has reached the criteria for judging deviations

## Slide 28: Progress management control
Progress confirmation meeting
In principle, attended by the project members
If necessary, the project manager or the stakeholders can attend
The progress of the development plan
The development and management activities
The status of implementation of requirement management, change management, and configuration management
The occurrence of risks, defects and AIs, and its status of correspondence.

## Slide 29
Q&A

## Slide 30
Renesas.com

## Slide 31
Revision | Description | Creator | Checker
1.00 | Newly created | Qui La | Nguyen Nguyen
2.00 | Added Change Management | Qui La | Nguyen Nguyen